CHURCH OF CENTRAL AFRICA PRESBYTERIAN (CCAP) – HEALTH DEPARTMENT

SYNOD OF LIVINGSTONIA

DAVID GORDON MEMORIAL HOSPITAL (DGMH)

P.O. Box 5

LIVINGSTONIA

MALAWI

Email: mbembablessings@gmail.com                                                                                                                                                                  16th March, 2026

Monitoring and Evaluation (M&E) Plans for Primary Health Care (PHC) Department Programs

April, 2026 – March, 2027

M&E Plan for Tuberculosis Program

| Programme Goal: Improve case detection and management of tuberculosis in the Livingstonia catchment area. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective 1: Increase the percentage of community members who have been screened for TB from 5% to 15% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Initiated TB screening services at the OPD | # of people screened for TB at the OPD | 1753 people | Activity report, site visits, registers | Every 3 months | TB coordinator, SHSA |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Increased uptake of TB screening services by community members | % of community members screened for TB | 15% | TB screening registers | Every 3 months | M&E Officer |
| Objective 2: Increase the percentage of people who have been screened for TB by SCPs from 9% to 12% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted TB screening by SCPs | # of screening people screened through SCPs | 300 people | TB screening registers | Every 3 months | M&E Officer |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Increased TB screening services by SCPs | % of people screened for SCPs | 15% | TB screening registers | Every 3 months | M&E Officer |
| Objective 2: Increase the percentage of hospital staff who have been screened for TB from 46% to 90% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted TB screening for staff at the hospital | # of staff screened for TB | 113 staff | Register, activity report | Twice a year | TB coordinator, SHSA |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Increased uptake of TB screening services by hospital staff | % of hospital staff screened for TB | 90% | TB screening register, activity report | Every 3 months | M&E Officer |

| Objective 3: Achieve at least 100% TB screening coverage among miners by the end of March 2027. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted TB screening at Kaziwiziwi coal mine | # of people screened | 326 miners | TB screening register, activity report | Every 6 months | M&E Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |

| Increased uptake of TB screening services by miners | % of miners screened for TB | At least 100% | Post-screening reports, site visits | Twice a year | M&E Officer |
| --- | --- | --- | --- | --- | --- |
| Objective 4: Achieve at least a 90% treatment success rate among those diagnosed with TB by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Provided TB treatment | # of patients received TB services | 30 people | Service delivery records | Every 3 months | TB coordinator, SHSA |
|  | # of patients cured | 27 people | Registers | Every 3 months | TB coordinator, SHSA |
|  | # of patients completed treatment (but no confirmation tests done) | 27 people | Register | Every 3 months | TB coordinator, SHSA |
|  | # of TB patients died | 0 person | Register | Every 3 months | TB coordinator, SHSA |
| Conducted follow-up | # of follow-ups conducted | 8 follow-ups | Registers | Every 3 months | TB coordinator, SHSA |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Increased adherence to TB drugs among patients | TB treatment success rate | At least 90% | TB treatment outcome reports | Every 3 months | M&E Officer |

| Objective 5: Enhance the capacity of TB volunteers in active case finding, contact tracing and follow-up by the end of March 2027. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted meetings with TB Volunteers | # of meetings conducted | 2 meetings | Meeting minutes Attendance sheets | Twice a year Quarterly | TB coordinator, SHSA TB coordinator, SHSA |
| Reviewed meetings with TB Volunteers | # of TB volunteers attended | 80 volunteers | Training reports Activity report | Quarterly Twice a year | TB coordinator, SHSA TB coordinator, SHSA |
| Conduct supportive supervision of sputum collection points. | # of supportive supervision of sputum collection points. | 12 supervisions | Activity report | Once per quarter | TB coordinator, SHSA |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |

| Enhanced capacity of volunteers in active case finding, contact tracing, and follow-up | # of volunteers capable of active case finding, contact tracing, and follow-up | 80 volunteers | Activity report | Twice a year | M&E Officer |
| --- | --- | --- | --- | --- | --- |

M&E Plan for HIV Testing Services (HTS) & Antiretroviral Therapy (ART) Program

| Programme Goal: Enhance equitable access to HIV testing and treatment services among the priority groups and underserved populations, and to improve treatment outcomes for people living with HIV in Livingstonia |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective 1: Increase the percentage of the priority groups accessing HIV testing services at DGMH from 95 % to 100% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted HTS outreach clinics. | # of outreach clinics conducted | 72 clinics | Monthly reports, Facility registers for outreach clinics | Every month | HTS & ART Focal person |
|  | # of clients accessing services from priority groups, i.e., pregnant women, people with other conditions) | 1500 people | Monthly reports, Facility registers for outreach clinics | Every month | HTS & ART Focal person |
| Provided static HTS services. | # of clients accessing HTS services from priority groups at Static | 1000 clients | Monthly reports, Facility registers for outreach clinics, attendance records | Every month | HTS & ART Focal person |
| Provided self-test kits. | # of kits distributed | 1000 kits | Distribution records, facility registers | Every month | HTS Provider |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Increased uptake of HTS services among priority groups | % of the priority population tested for HIV | At least 100% | HTS & ART monthly summary reports | Every 3 months | M&E Officer |
| Objective 2: Increase the percentage of underserved populations accessing HIV testing services at DGMH from 30 % to 60% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted HTS outreach clinics. | # of clients accessing services from underserved populations i.e. (men, youth, sex workers, students etc.) | 1800 people | Monthly reports, Facility registers for outreach clinics | Every month | HTS & ART Focal person |
| Provided static HTS services. | # of clients accessing HTS services from underserved groups at Static | 1200 clients | Monthly reports, Facility registers for outreach clinics, attendance records | Every month | HTS & ART Focal person |
| Provided self-test kits. | # of self-test kits provided | 1500 kits | Reports, HTS registers | Every 3 months | HTS & ART Focal person |
|  | # of clients received kits | 800 clients | Reports, HTS registers | Every 3 months | HTS & ART Focal person |
| Conducted integrated HTS campaigns. | # of integrated HTS campaigns conducted | 12 campaigns | Distribution records, facility registers | Every 3 months | HTS & ART Focal person |
|  | # of clients attended HTS campaign | 2000 clients | Distribution records, facility registers | Every 3 months | HTS & ART Focal person |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Increased HTS uptake among the underserved | % of the underserved group accessed HTS services | At least 60% | HTS registers | Every 3 months | M&E Officer |

| Objective 3: Increase the percentage of people accessing ART at DGMH from 64% to 95% by the end of March 2027. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Initiated ART for new clients | # of clients initiated on ART | 40 clients | ART registers | Every 3 months | HTS & ART Focal person |
| Dispensed ART for old clients | # of old patients receiving ARTs | 400 clients | ART registers | Every 3 months | HTS & ART Focal person |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |

| Increased number of people accessing ART at DGMH | % of people accessing ART | At least 95% | ART register | Every 3 months | M&E Officer |
| --- | --- | --- | --- | --- | --- |
| Objective 4: Increase the percentage of people adhering to ART at DGMH from 85% to 95% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Collected viral load samples. | # of collected samples | 232 samples | Reports, HTS registers, | Every 3 months | HTS & ART Focal person |
|  | # of samples with suppressed results | 220 samples | Reports, HTS registers | Every 3 months | HTS & ART Focal person |
|  | # of samples with high viral load | 12 samples | Distribution records, facility registers | Every 3 months | HTS & ART Focal person |
|  | # of samples rejected/missed | 0 samples | Distribution records, facility registers | Every 3 months | HTS & ART Focal person |
| Conducted pill counting for clients. | # of clients adhering to ART through pill count | 220 clients | EMR | Every 3 months | HTS & ART Focal person |
| Followed up with patients on ART | # of patients followed up | 10 clients | Facility registers | Every 3 months | HTS & ART Focal person |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved ART adherence | % of people adhering to ART | At least 95% | ART registers | Every 3 months | M&E Officer |
| Objective 5: Equip at least 80% of the People Living with HIV (PLHIV) club members with financial literacy and income-generating skills by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Trained club members of PLHIV on financial management and resource mobilization | # of trainings conducted | 2 trainings | Reports | Once a year | HTS & ART Focal person |
|  | # of club members of PLHIV trained on financial management and resource mobilization | 50 members | Reports, attendance sheets | Twice a year | HTS & ART Focal person |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved financial management and resource mobilization among club members of PLHIV | % of club members of PLHIV with financial management and resource mobilization skills | At least 80% | Activity reports | Every 3 months | M&E Officer |

M&E Plan for Expanded Programme Immunization (EPI)

| Programme Goal: Improve immunization coverage in the Livingstonia catchment area. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 1: Increase the percentage of fully immunized children from 97% to 100% by the end of March 2027. |  |  |  |  |  |  |  |
| Outputs | Indicator | Target |  |  | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted vaccination clinics (outreaches and static) | # of outreach vaccination clinics conducted | 192 outreach clinics |  |  | HSAs quarterly report EPI Register | Every 3 months | Senior HSA; EPI Focal Person |
|  | # of static vaccination clinics conducted | 240 static clinics |  |  | HSAs quarterly report EPI Register | Every 3 months | Senior HSA; EPI Focal Person |
|  | # of under-fives accessed immunization services | 2646 under fives |  |  | HSAs quarterly report | Every 3 months | Senior HSA; EPI Focal Person |
|  | # of under-ones fully immunised | 778 under ones |  |  | HSAs quarterly report EPI Register | Every 3 months | Senior HSA; EPI Focal Person |
| Re-oriented EPI volunteers | # of EPI volunteers re-oriented | 40 volunteers |  |  | Orientation attendance sheet | Every 6 months | Senior HSA; EPI Focal Person |
|  | # of reorientations conducted | 2 Reorientations |  |  | Activity report | Every 6 months | Senior HSA; EPI Focal Person |
| Conducted refresher training on defaulter tracing | # of EPI volunteers trained | 40 volunteers |  |  | Training sheet | Every 6 months | Senior HSA; EPI Focal Person |
|  | # of refresher training | 2 refreshers |  |  | Activity report | Every 6 months | Senior HSA; EPI Focal Person |
| Outcomes | Indicator | Target |  |  | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Increased vaccine uptake among under-ones. | % of under-ones fully immunized | At least 97% - 100% |  |  | HSAs quarterly report | Every 3 months | M&E officer |
| Objective 2: Achieve 100% of girls aged 9 years who have received the HPV vaccine by the end of March 2027. |  |  |  |  |  |  |  |
| Outputs | Indicator | Target |  |  | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Provided immunizations in schools. | # of schools reached for Immunization services | 17 schools |  |  | Activity report | Every 3 months | EPI Focal Person |
|  | # of girls (9 years) vaccinated in schools | 311 girls |  |  | EPI register Activity reports HSA quarterly reports. | Every 3 months | EPI Focal Person |
| Conducted defaulter tracing for HPV | # of 9years girls traced | 100 girls |  |  | Activity reports HSAs Quarterly report | Every 3 months | EPI Focal Person |
| Outcomes | Indicator | Target |  |  | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Increased HPV uptake among girls aged 9 years. | % of girls aged 9 years) who received the HPV vaccine | At least 100% |  |  | EPI reports | Every 6 months | M&E Officer |
| Objective 3: Increase the percentage of women at reproductive age who have received TD from 31% to 50% by the end of March 2027. |  |  |  |  |  |  |  |
| Outputs | Indicator |  | Target | Data Source (method/tool) |  | Frequency of data collection | Responsible Person(s) |
| Provided TD vaccines | # of pregnant women vaccinated |  | 778 pregnant women | EPI & Antenatal reports |  | Quarterly | EPI Focal Person & Community Nurse |
|  | # of non-pregnant women vaccinated |  | 2801 non-pregnant women | EPI & Antenatal reports |  | Quarterly | Senior HSA and EPI Focal Person |
| Conducted defaulter tracing for TD. | # of non-pregnant women traced |  | 1000 non-pregnant women | EPI & Antenatal reports |  | Quarterly | Senior HSA and EPI Focal Person |
| Outcomes | Indicator |  | Target | Data Source (method/tool) |  | Frequency of data collection | Responsible Person(s) |
| Increased TD uptake among women of reproductive age. | % of women at reproductive age who were vaccinated |  | At least 50% | EPI reports |  | Every 6 months | M&E Officer |

M&E Plan for Integrated Management of Childhood Illnesses (IMCI)

| Programme Goal: To reduce illnesses and preventable deaths among children under the age of five in Livingstonia. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective 1: Integrate and operationalize the nutrition component of IMCI by 100% of the IMCI clinics by the end of March 2026. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Commenced nutrition services in IMCI clinics. | # of IMCI clinics providing quality nutrition service | 6 IMCI clinics | Activity report, IMCI register, nutrition register | Every quarter | IMCI Coordinator |
|  | # of children accessing nutrition services in IMCI Clinics | 2646 under-five children | Activity report, IMCI register, nutrition register | Every quarter | IMCI Coordinator |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved detection and management of malnutrition among under-fives | % IMCI clinics providing quality nutrition service | 100% | Activity report, IMCI register, nutrition register | Twice a year | M & E Officer |
| Objective 2: Increase access to IMCI services among under-fives from 52% to 70% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Provided IMCI services | # of IMCI clinics providing services | 6 clinics | IMCI registers and monthly report | Every month | IMCI Coordinator |
|  | # of children accessing IMCI services | 1852 under-five children | IMCI registers and monthly reports | Every month | IMCI Coordinator |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved case management and treatment of childhood illnesses. | % of under-five children with childhood illnesses managed and treated according to national IMCI guidelines | At least 95% | Quarterly report | Every quarter | M & E Officer |
| Objective 3: Ensure that 95% of under-five children presenting IMCI-related conditions in target areas are correctly assessed and managed according to IMCI guidelines by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted on-the-job mentorship and supervision for HSAs providing IMCI services | # of children correctly assessed | 2514 children | Supervision report | Once a quarter | IMCI Coordinator |
|  | # of children correctly managed | 2514 children | Supervision report | Once a quarter | IMCI Coordinator |
|  | # of supervision conducted | 6 supervisions | Supervision report | Once a quarter | IMCI Coordinator |
|  | # of IMCI clinics supervised | 6 IMCI clinics | Activity report | Twice a year | Senior HSA |
|  | # of mentorship sessions conducted | 2 sessions | Activity report | Twice a year | PHC director |
|  | # of HSAs mentored | 13 HSAs | Mentorship sheet | Every quarter | IMCI Coordinator |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved case management and treatment of childhood illnesses. | % of under-five children with childhood illnesses managed and treated according to national IMCI guidelines | At least 95% | Quarterly report | Every quarter | M & E Officer |

M&E Plan for Maternal & Child Health (MCH) Program

| Programme Goal: Improve access to and utilization of cervical cancer screening, antenatal care, and family planning services for women and young people accessing Maternal and Child Health (MCH) services at DGMH within the Livingstonia catchment area. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 1: Increase the percentage of eligible women screened for cervical cancer in the Livingstonia community from 9% to 15 % by the end of March 2027. |  |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted cervical cancer screening in communities | # of cervical cancer screening sessions conducted in the communities. | 8 community screening sessions | Activity reports, cervical cancer screening records | Every 3 months | Community Health Nurse |
|  | # of women screened for cervical cancer during screening sessions in the communities | 160 women | Activity reports, cervical cancer screening registers | Every 3 months | Community Health Nurse |
| Conducted cervical cancer screening in schools | # of cervical cancer screening sessions conducted in schools. | 6 schools' screening sessions | Screening records and reports | Every 3 months | Community Health Nurse |
|  | # of female students screened for cervical cancer screening in schools | 90 female students | Screening records and reports | Every 3 months | Community Health Nurse |
| Conducted cervical cancer screening at the hospital | # of cervical cancer screenings conducted at the hospital. | 60 screening sessions | Activity reports, cervical cancer screening registers | Once every month | Community Health Nurse |
|  | # of women screened for cervical cancer at the hospital | 100 women | Screening registers | Once every month | Community Health Nurse |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Increased uptake of cervical cancer screening | % of eligible girls and women screened for cervical cancer | At least 15% | Screening records, Activity reports, departmental reports | Every 3 months | M&E Officer |
| Objective 2: Increase the percentage of pregnant women attending antenatal services at DGMH who receive the recommended four or more antenatal care visits from 22% to 50% by the end of March 2027. |  |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted antenatal clinics | # of antenatal clinics conducted | 192 static antenatal clinics 72 outreach antenatal clinics | Antenatal registers, MCH reports Antenatal registers, MCH reports | Once every month Once every month | Community Health Nurse Community Health Nurse |
|  | # of pregnant women receiving antenatal care services | 2000 pregnant women | Antenatal registers, MCH reports | Once every month | Community Health Nurse |
|  | # of pregnant women attending four or more antenatal care visits | 600 pregnant women | Antenatal registers, MCH reports | Once every month | Community Health Nurse |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Increased antenatal care attendance among pregnant women | % of pregnant women attending four or more antenatal care visits | At least 50% | Antenatal care services records, MCH reports | Every 3 months | M&E Officer |

| Objective 3: Sustain the modern contraceptive prevalence rate among women of reproductive age accessing services at DGMH at 95% by the end of March 2027. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Provided family planning services. | # of Women receiving family planning services | 2470 women | Family planning records and reports | Once every month | Community Health Nurse |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |

| Increased uptake of modern contraceptive methods among women | % of women accessing modern contraceptive services at DGMH | At least 95% | Family planning records, MCH reports | Every 3 months | M&E Officer |
| --- | --- | --- | --- | --- | --- |

M&E Plan for Nutrition Program

| Programme Goal: Reduce malnutrition prevalence among children under the age of five, pregnant and lactating women in Livingstonia. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective 1: Increase adoption of recommended feeding practices among caregivers from 50% to 80% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted cooking demonstrations | # of cooking demonstrations conducted | 4 cooking demonstrations. | Activity report | Once every 3 months | Nutrition Officer |
|  | # of caregivers who attend cooking demonstrations | 430 caregivers | Activity report | Once every 3 months | Nutrition Officer |
| Commemorated World Nutrition Day | # of commemorations | 1 Commemoration | Activity report | Once a year | Nutrition Officer |
|  | # of people who attend the commemoration | 200 people | Activity report | Once a year | Nutrition Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved feeding practices among caregivers. | % of caregivers adhering to recommended feeding practices | 80% of caregivers (400) | Household surveys, Caregiver interviews, reports | Every 6 months | M&E Officer |
| Objective 2: Increase the percentage of under-five children whose malnutrition is detected and managed early from 92% to 99% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted mass nutrition screening. | # of children screened for malnutrition | 2,000 children | Screening records, activity report | Every 3 months | Nutrition Officer |
| Conducted defaulter tracing | # of defaulters traced | 10 defaulters | Activity report, defaulter tracing forms | Every 3 months | Nutrition Officer |
| Conducted OTP clinics | # of clinics conducted | 48 clinics | Registers, reports | Every 3 months | Nutrition Officer |
|  | # of malnourished children | 50 children | Registers, reports | Every 3 months | Nutrition Officer |
|  | # of children cured | 49 children | Registers, reports | Every 3 months | Nutrition Officer |
|  | # of children died | 0 children | Registers, reports | Every 3 months | Nutrition Officer |
| Conducted SFP clinics | # of staff trained in SFP | 20 staff | Activity report | Every 3 months | Nutrition Officer |
|  | # of children enrolled | 132 children | Registers, reports | Every 3 months | Nutrition Officer |
|  | # of children cured | 132 children | Registers, reports | Every 3 months | Nutrition Officer |
|  | # of children died | 0 children | Registers, reports | Every 3 months | Nutrition Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Strengthened early detection and management of malnutrition among under-fives. | Percentage of under-five children with malnutrition detected and managed early | At least 75% of U-5 children are detected and managed early | Activity report, nutrition register | Every 3 months | M&E Officer |
| Objective 3: Increase the percentage of pregnant women and lactating mothers whose malnutrition is detected and managed early by 50% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted nutrition screening of pregnant women | # of pregnant women screened for malnutrition | 330 women | Screening and activity report | Every 3 months | Nutrition Officer |
|  | # of malnourished pregnant women | 15 women | Activity report, registers | Every 3 months | Nutrition Officer |
|  | # of pregnant women managed for malnutrition | 15 women | Activity report, registers | Every 3 months | Nutrition Officer |
| Conducted nutrition screening of lactating women | # of lactating women screened for malnutrition | 650 women | Activity report, registers | Every 3 months | Nutrition Officer |
|  | # of malnourished lactating women | 18 women | Registers, reports | Every 3 months | Nutrition Officer |
|  | # of lactating women managed for malnutrition | 18 women | Registers, reports | Every 3 months | Nutrition Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Strengthened early detection and management of malnutrition among pregnant and lactating women | Percentage of women whose malnutrition was detected and managed early | 50% | Reports, registers | Every 3 months | M&E Officer |

M&E Plan for Environmental Health Program

| Programme Goal: To improve environmental health and safeguard patients, staff, and communities from foodborne, WASH-related, occupational risks and hazards, vector borne and NTD diseases. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective 1: To increase compliance with food safety and hygiene standards among food establishments from 20% to 50% by the end of March 2027 |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted food inspections | # of food premises inspected | 28 food premises | Inspections report | Twice a year | WASH Officer |
| IEC materials lobbied | # of IEC materials lobbied | 15 posters | Health education report | Twice a year | WASH Officer |
| Trained food premise owners in FSN | # of food premise owners trained | 28 food owners | Training report | Once a year | WASH Officer |
| Inspection checklist reviewed | # of inspection checklists reviewed | 1 checklist | Inspections report | Once a year | WASH officer |
| Conducted meat inspection | # of inspections conducted | 4 inspections | Inspections report | Once per quarter | WASH Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved food safety and hygiene practices in food establishments. | % of food establishments complying with food safety and hygiene standards. | At least 50% | FSH reports | Twice a year | M&E Officer |
| Objective 2: To increase access to safe water, improved sanitation facilities, and hygienic services from 55% to 70% by the end of march, 2027 |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Distributed chlorine in households | # of households received | 4,108 households | Activity report | Twice a year | WASH Officer |
| Conducted water quality testing in communities | # of water samples tested | 30 samples (1 from each community) | Test results and reports | Twice a year | WASH Officer |
| Maintained shallow wells in communities | # of shallow wells maintained | 8 shallow wells | Maintenance reports, observation, site visits | Twice a year | WASH Officer |
| Installed shallow wells in the community | # of shallow wells installed | 5 shallow wells | Installation reports, observation, site visits | Twice a year | WASH Officer |
| Conducted water tank clean-up exercises | # of water tank clean-up exercises conducted | 4 exercises | Cleaning exercise reports | Once per quarter | WASH Officer |
|  | # of water tanks cleaned | 4 tanks | Cleaning exercise reports | Once per quarter | WASH Officer |
| Conducted village inspections Inspected sanitary facilities in public institutions | # of village inspections conducted # of public institutions inspected | 15 villages 17 institutions | Inspections report Inspections report | Once per quarter Once per quarter | WASH Officer WASH Officer |
| Conducted health education on WASH | # of health education sessions conducted | 20 sessions | Health education report | Every month | WASH Officer |
| Conducted integrated awareness campaigns | # of integrated awareness campaigns conducted | 4 campaigns | Integrated awareness report | Once per quarter | WASH Officer |
| Commemorated World Toilet, Water, Hand Hygiene & Menstrual Hygiene Days | # of commemorations conducted | 4 commemorations | Commemorations report | Once per quarter | WASH Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved access to safe water, sanitation facilities, and hygienic practices in the community | % of households with access to safe water, improved sanitation facilities, and practicing proper hygiene. | At least 70% | Activity reports | Twice a year | M&E Officer |

| Objective 3: To increase compliance with occupational health and safety standards among workplaces and public institutions from 30% to 50% by Mach, 2027 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Updated work place list | # of updated workplace list | 1 list | OHS report | Once a year | WASH Officer |
| Checklists reviewed | # of checklists reviewed | 1 checklist | OHS report | Once a year | WASH Officer |
| Conducted workplace inspections | # of workplace inspections conducted | 20 workplaces | Inspections report | Twice a year | WASH Officer |
| Conducted HCWM inspections | # of HCWM inspections conducted | 24 inspections | Inspections report | Every month | WASH Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |

| Improved environmental health and safety in workplaces and public institutions. | % of workplaces and public institutions complying with environmental health and safety standards. | At least 50% | Assessment reports | Twice a year | M&E Officer |
| --- | --- | --- | --- | --- | --- |

| Objective 4: To Scale up malaria prevention and control measures from 85% to 95% by March 2027. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted routine malaria surveillance at DGMH. | # of surveillance conducted | 52 Sessions | Reports, Registers | Once a week | Malaria coordinator |
| Provide nets to priority groups i.e. pregnant women | # of nets given | 2000 Nets | Reports, Registers | Once a week | MCH coordinator |
|  | # of clients received nets | 2000 Clients | Reports, Registers | Once a week | MCH coordinator |
| Conducted health education on malaria strategies, net hanging demonstrations | # of health education sessions | 8 sessions | Activity reports | Once per month | Malaria coordinator |
| Conducted net integrity survey | # of surveys conducted | 1 survey | Activity report, Observations | Once a year | Malaria coordinator |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved uptake of malaria prevention and control strategies | % of population with enhanced knowledge on malaria prevention and control strategies | At least 95% | Reports, Field visits | Every 3 months | M&E Officer |
| Objective 5: To increase access to and uptake of schistosomiasis prevention, control and treatment services in endemic communities |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted mass screening in endemic communities | Number of people screened | 386 people | Activity report | Annually | WASH Officer |
|  | Number of people who tested positive | - | Activity report | Annually | WASH Officer |
|  | Number of people who tested positive | - | Activity report | Annually | WASH Officer |
| Conducted awareness campaigns in endemic communities | Number of campaigns conducted | 6 campaigns | Activity report | Quarterly | WASH Officer |
|  | Number of people reached | 4000 people | Activity report | Quarterly | WASH Officer |
| Conducted surveillance of schistosomiasis | Number of surveillance reports | 52 reports | Surveillance reports | Weekly | Surveillance Officer |
| Provided treatment to patients | Number of patients who received treatment | - | Activity report | Quarterly | WASH Officer |
|  | Number of people cured | - | Activity report | Quarterly | WASH Officer |
| Conducted mass drug administration of praziquantel | Number of people reached | - | Activity report | Annually | WASH Officer |
|  | Number of tablets provided | - | Activity report | Annually | WASH Officer |
|  | Number of communities benefited | - | Activity report | Annually | WASH Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved uptake of schistosomiasis prevention, control and treatment services in endemic communities | % proportion of people with improved uptake of schistosomiasis prevention, control and treatment services in endemic communities | - | Registers, activity reports, surveillance reports | Annually | WASH Officer |

M&E Plan for Community Engagement Program

| Programme Goal: Strengthen community engagement in healthcare programs in Livingstonia. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective 1: Improve community participation in healthcare programs in all catchment areas in Livingstonia from 70% to 95% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted regular Hospital Management Committee (HMC) meetings. | # of Meetings conducted | 4 Meetings | Meeting minutes, Participants list | Once every 3 months | CE Officer |
|  | # of Participants | 16 Participants | Meeting minutes, Participants list | Once every 3 months | CE Officer |
| Finalized formation of Village Health Committees (VHCs). | # of VHCs formed | 1 committee | Activity reports, Participants list | Once a year | CE Officer |
|  | # of VHCs members | 10 members | Activity reports, Participants list | Once a year | CE Officer |
| Trained all VHCs | # of VHCs members | 110 VHCs | Activity reports, Participants list | Once a year | CE Officer |
|  | # of Trainings conducted | 11 Sessions | Activity reports, Participants list | Once a year | CE Officer |
|  | # of CHAG s formed | 1 CHAGs | Activity reports, Participants list | Once a year | CE Officer |
| Trained all CHAG | # of CHAGs trained | 2 CHAGs | Activity reports, Participants list | Once a year | CE Officer |
|  | # of CHAG members trained | 30 Members | Reports, participants list | Once a year | CE Officer |
| Attended ADCs meetings | # of ADCs attended | 24 meetings | Reports, participants list | Every month | CE Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improve the participation of the community in health care programs. | Level of community satisfaction with opportunities to participate in healthcare programs | At least 95% | Surveys | Once a year | M&E Officer |
| Objective 2: Strengthen capacity building for all community structures in Livingstonia from 67% to 95% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted capacity-building workshops for VHC members | # of workshops conducted | 4 workshops | Workshop reports, Participants list, | Once every 3 months | CE Officer |
|  | # of Participants | 220 Participant | Workshop reports, Participants list, | Once every 3 months | CE Officer |
| Conducted capacity-building workshops for CHAG members | # of workshops conducted | 4 workshops | Workshop reports, Participants list, | Once every 3 months | CE Officer |
|  | # of Participants | 240 Participant | Workshop reports, Participants list, | Once every 3 months | CE Officer |
| Conducted an award ceremony for CHAGs and VHCs | # of award ceremony | 1 ceremony | Activity reports, Participants list | Once a year | PHC Director/ CE Officer |
| Conducted CHAG and VHC review meetings | # of CHAG review meetings conducted | 16 meetings | Reports, participants list | Twice a year | CE Officer |
|  | # of Participants | 240 Participants | Reports, participants list | Twice a year | CE Officer |
|  | # of VHC review meeting conducted | 22 meetings | Reports, participants list | Twice a year | CE Officer |
|  | # of Participants | 220 Participants | Reports, participants list | Twice a year | CE Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved understanding of the need to take part in healthcare programs and ensure sustainability | % of the population with an understanding of taking part in healthcare programs | At least 95% | Surveys, workshops | Once a year | M&E Officer |

M&E Plan for Health Promotion

| Programme Goal: Improve the overall health and well-being of communities through sustained adoption of positive health behaviours in Livingstonia. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective 1: Increase the percentage of community members demonstrating improved knowledge across PHC thematic areas (WASH, MCH, OHS, Nutrition, HIV/ART, etc.) from 63 % to 80% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted integrated health education sessions. | # of integrated sessions conducted # of people reached | 350 sessions 12,000 people | Session reports Session reports | Once every quarter Once every quarter | SBCC Officer SBCC Officer |
| Conducted integrated awareness campaigns | # of integrated campaigns conducted # of people reached | 20 campaigns 6,500 people | Campaign reports Campaign reports | Once every quarter Once every quarter | SBCC Officer SBCC Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Increased understanding of health issues among community members | % of community members with increased knowledge across PHC thematic areas | 80% | Focus group discussions, Knowledge, Attitude and Practice studies | Every six months | M&E Officer |
| Objective 2: Increase the adoption of key health practices across PHC thematic areas (WASH, MCH, OHS, Nutrition, HIV/ART, etc) from 40 % to 60% by the end of March 2027 |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Developed an integrated SBCC Strategy for Primary Health Care Programs | Availability of the SBCC Strategy document | 1 strategy | SBCC strategy document review | One-time | SBCC Officer |
| Conducted assessment & produced report using SBCC Score Card | # of assessments conducted | 12 assessments | SBCC Score card | Every month | SBCC Officer |
|  | # of reports submitted to PHC Director & DHO | 12 reports | Activity reports | Every month | PHC Director |
| Conducted a KAP study | # of KAP study conducted | 2 studies | Activity reports | Twice a year | SBCC Officer/ M&E Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Increased adoption of positive health practices among community members | % of community members adopting positive health practices | At least 60% | Households’ Observational Checklists | Every six months | M&E Officer SBCC Officer |

M&E Plan for Youth Program

| Programme Goal: Empower youth in Livingstonia with knowledge, life skills and platforms to promote health behaviors and make informed decisions in Livingstonia. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective 1: Reduce teenage pregnancies in targeted communities by 45% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Train peer educators in targeted communities with high teenage pregnancy. Engaged community leaders to develop bylaws to prevent teenage pregnancies | # of trainings conducted # of trained peer educators in targeted communities with high teenage pregnancies # of engagement meetings conducted | 2 trainings 13 peer educators 1 engagement meetings | Training Reports Training attendance sheet Meeting minutes | Every 3 months Every 3 months Twice a year | SBCC Officer SBCC Officer SBCC Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Reduced rates of teenage pregnancies | % of reduced rates of teenage pregnancies | At least 45% | Training reports, activity reports, surveys | Twice a year | M&E officer |
| Objective 2: Increase the percentage of youths with accurate knowledge about HIV, SRHR, behavior change communication and nutrition from 75% to 90% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Formed new youth clubs in catchment areas with high teenage pregnancies. Trained new youth clubs in catchment areas with high teenage pregnancies. | # of newly formed youth clubs. # of new youth clubs trained | 2 youth clubs 2 youth clubs | Activity reports, youth club visits Training Reports | Twice a year Twice a year | SBCC Officer SBCC Officer |

| Conducted refresher Training of old youth clubs in HIV, SRHR, behavior change communication and nutrition. | # refresher training conducted # of youths attended | 6 youths 60 youths | Activity reports Attendant sheets’ | Twice a year Twice a year | SBCC Officer SBCC Officer |
| --- | --- | --- | --- | --- | --- |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved understanding of youth clubs on nutrition, SRHR, HIV and BC. | % of Improved understanding of youth clubs on nutrition, SRHR, HIV and BC | At least 90% | Training reports | Twice a year | M&E Officer |

M&E Plan for Agriculture Program (Tikolole Project)

| Programme Goal: Enhance the livelihoods of club farmers through sustainable crop farming, fish farming and animal rearing in the Livingstonia catchment area. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 1: Strengthen the capacity of 315 club farmers in irrigation farming, animal rearing and fish farming by the end of March 2027. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outputs | Indicator |  |  | Target |  |  | Data Source (method/tool) |  |  | Frequency of data collection |  |  | Responsible Person(s) |  |
| Conducted refresher training of fish farmers on fishing. | # of the trainings conducted |  |  | 1 training |  |  | Training reports |  |  | Once per year |  |  | Agriculture Officer |  |
|  | # of fish farmers trained |  |  | 30 fish farmers |  |  | Attendance sheets |  |  | Once per year |  |  | Agriculture Officer |  |
| Conducted field visits for the irrigation club farmers. | # of field visits conducted |  |  | 4 visits |  |  | Field visit reports |  |  | Every 3 months |  |  | Agriculture Officer |  |
|  | # of clubs visited |  |  | 6 irrigation clubs |  |  | Field visit reports |  |  | Every 3 months |  |  | Agriculture Officer |  |
| Conducted field visits for fish farmers. | # of field visits conducted |  |  | 4 visits |  |  | Field visit reports |  |  | Every 3 months |  |  | Agriculture Officer |  |
|  | # of fish farmers visited |  |  | 30 fish farmers |  |  | Field visit reports |  |  | Every 3 months |  |  | Agriculture Officer |  |
| Conducted review meetings for irrigation farmers. | # of the meetings conducted |  |  | 1 meeting |  |  | Meeting minutes |  |  | Once per year |  |  | Agriculture Officer |  |
|  | # of the farmers attended |  |  | 12 farmers |  |  | Attendance sheets |  |  | Once per year |  |  | Agriculture Officer |  |
| Conducted review meetings for animal rearing farmers. | # of review meetings |  |  | 1 meeting |  |  | Meeting minutes |  |  | Once per year |  |  | Agriculture Officer |  |
|  | # of the farmers attending |  |  | 6 farmers |  |  | Attendance sheets |  |  | Once per year |  |  | Agriculture Officer |  |
| Conducted review meetings for fish farmers. | # of the meetings conducted |  |  | 1 meeting |  |  | Meeting minutes |  |  | Once per year |  |  | Agriculture Officer |  |
|  | # of the farmers attended |  |  | 30 farmers |  |  | Attendance sheets |  |  | Once per year |  |  | Agriculture Officer |  |
|  | # of field visits conducted |  |  | 4 visits |  |  | Field visit reports |  |  | Every 3 months |  |  | Agriculture Officer |  |
|  | # of the farmers visited |  |  | 6 farmers |  |  | Field visit reports |  |  | Every 3 months |  |  | Agriculture Officer |  |
| Outcomes | Indicator |  |  | Target |  |  | Data Source (method/tool) |  |  | Frequency of data collection |  |  | Responsible Person(s) |  |
| Improved capacity of the farmers. | # of farmers demonstrating improved knowledge and skills |  |  | 315 club farmers |  |  | Field visits, Project reports |  |  | Twice a year |  |  | M&E Officer |  |
| Objective 2: By the end of March 2027, improve timely access to quality farm inputs for 100% of the irrigation club farmers before the irrigation season begins |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outputs | Indicator |  |  | Target |  |  | Data Source (method/tool) |  |  | Frequency of data collection |  |  | Responsible Person(s) |  |
| Purchased and distributed fertilizer. | Number of fertiliser bags purchased |  |  | 86 bags of Urea 77 bags of NPK |  |  | Procurement records |  |  | Once a year |  |  | Agriculture Officer |  |
|  | Timeliness of the purchase and distribution of fertiliser |  |  | At least 2 months before the irrigation season begins |  |  | Activity reports, delivery notes |  |  | Once a year |  |  | Agriculture Officer |  |
| Purchased seeds | Number of maize seed packets purchased |  |  | 232 packets |  |  | Procurement records |  |  | Once a year |  |  | Agriculture Officer |  |
| Distributed seeds | Number of maize seed packets distributed |  |  | 232 packets |  |  | Activity reports, delivery notes |  |  | Once a year |  |  | Agriculture Officer |  |
| Outcomes | Indicator |  |  | Target |  |  | Data Source (method/tool) |  |  | Frequency of data collection |  |  | Responsible Person(s) |  |
| Enhanced timely access to farm inputs | Percentage of farmers reporting the timely availability of farm inputs |  |  | 100% of farmers |  |  | Project reports, farmers' surveys |  |  | Once per year |  |  | M&E Officer |  |
| Objective 3: Promote sustainability and ownership of farming clubs by the end of March 2027. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outputs |  | Indicator |  |  | Target |  | Data Source (method/tool) |  | Frequency of data collection |  |  | Responsible Person(s) |  |  |  |
| Registered farmers in cooperatives |  | # of farmers registered |  |  | 315 farmers |  | Registration certificate |  | Once per year |  |  | Agriculture Officer |  |  |  |
|  |  | # of fish farmers registered |  |  | 45 farmers |  | Registration certificate |  | Once per year |  |  | Agriculture Officer |  |  |  |
|  |  | # of irrigation farmers registered |  |  | 219 farmers |  | Registration certificate |  | Once per year |  |  | Agriculture Officer |  |  |  |
|  |  | # of animal-rearing farmers registered |  |  | 51 farmers |  | Registration certificate |  | Once per year |  |  | Agriculture Officer |  |  |  |
| Objective 4: To engage in fruit production by March, 2027 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Purchase of fruit trees |  | Number of orange trees purchased |  |  | 100 oranges |  | Procurement records, Activity reports |  | Once per quarter |  |  | Agriculture Officer |  |  |  |
|  |  | Number of tangerines purchased |  |  | 100 tangerines |  | Procurement records, Activity reports |  | Once per quarter |  |  | Agriculture Officer |  |  |  |
|  |  | Number of apple trees purchased |  |  | 100 apples |  | Procurement records, Activity reports |  | Once per quarter |  |  | Agriculture Officer |  |  |  |
|  |  | Number of lemon trees purchased |  |  | 100 lemons |  | Procurement records, Activity reports |  | Once per quarter |  |  | Agriculture Officer |  |  |  |
| Outcomes |  | Indicator |  |  | Target |  | Data Source (method/tool) |  | Frequency of data collection |  |  | Responsible Person(s) |  |  |  |
| Increased fruit production |  | - |  |  | - |  | Procurement records, Activity reports |  | Once per year |  |  | Agriculture Officer |  |  |  |
| Objective 5: By the end of March 2027, increase the number of livestock at PHC farm to boost income |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outputs |  |  | Indicator |  |  | Target |  | Data Source (method/tool) |  |  | Frequency of data collection |  |  | Responsible Person(s) |  |
| Constructed pig housing |  |  | Number of houses constructed |  |  | 1 house |  | Activity report |  |  | Once a year |  |  | Agriculture officer |  |
| Purchased Rabbits |  |  | Number of Rabbits timely purchased |  |  | 10 Rabbits |  | Procurement records, Activity report |  |  | Once per quarter |  |  | Agriculture Officer |  |
| Purchased pigs |  |  | Number of Pigs purchased |  |  | 3 pigs |  | Procurement records, Activity reports |  |  | Once per quarter |  |  | Agriculture Officer |  |
| Purchased Chickens |  |  | Number of Chickens purchased |  |  | 30 chickens |  | Procurement records, Activity report |  |  | Once per quarter |  |  | Agriculture Officer |  |
| Purchased Ducks |  |  | Number of Ducks purchased |  |  | 5 Ducks |  | Procurement records, Activity reports |  |  | Once per quarter |  |  | Agriculture Officer |  |
| Harvested Fish |  |  | Number of times fish are harvested |  |  | 2 times |  | Activity report |  |  | Twice a year |  |  | Agriculture Officer |  |
| Outcomes |  |  | Indicator |  |  | Target |  | Data Source (method/tool) |  |  | Frequency of data collection |  |  | Responsible Person(s) |  |
| Increased animal production |  |  | - |  |  | - |  | Project reports, farmers' surveys |  |  | Once per year |  |  | M&E Officer |  |

M&E Plan for Outbreak Preparedness & Response Program

| Programme Goal: Improve outbreak preparedness and response in the Livingstonia catchment area. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective 1: Increase capacity to detect outbreaks by ensuring 95% daily data collection and analysis by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Conducted routine data collection, analysis and reporting. | # of weekly reports submitted per year | 52 reports | Surveillance reports, registers DHIS2 | Once per day | Surveillance Officer/IDSR Coordinator |
|  | # of monthly reports submitted per year | 12 reports | Surveillance reports, registers DHIS2 | Once per week | Surveillance Officer/IDSR Coordinator |
|  | # of quarterly reports submitted per year | 4 reports | Surveillance reports, registers DHIS2 | Once per month | Surveillance Officer/IDSR Coordinator |
| Reported signals through OHSP. | # of signals reported through OHSP | 6 signals | Surveillance Forms | On time of detection | Surveillance Officer/IDSR Coordinator |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Improved timely disease surveillance | % of surveillance reports received | At least 95% | Surveillance reports | Once per week | M&E Officer |
| Objective 2: Strengthen outbreak preparedness and response from 60% to 80% by the end of March 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Trained all HSAs in outbreak preparedness and response. | # of trainings conducted | 2 trainings | Training reports, | Twice a year | Surveillance Officer/ PHC Director |
|  | # of HSAs attended the training | 15 HSAs | Attendance sheet | Twice a year | Surveillance Officer/ PHC Director |
| Constituted an outbreak preparedness and response team | # of Outbreak preparedness and response team | 1 team | Activity report | Once a year | Surveillance Officer/ Hospital Director |
| Oriented the outbreak preparedness and response team | # of reorientation sessions conducted | 2 sessions | Attendance sheet | Twice a year | Surveillance Officer |
|  | # of team members oriented | 10 team members | Activity report | Twice a year | Surveillance Officer |
| Conducted volunteer refresher training on EBS | # of volunteer refresher training on EBS conducted # of volunteers attended | 2 refresh trainings 28 members | Attendance sheet Attendance sheet | Twice a year Twice a year | Surveillance Officer Surveillance Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Enhanced capacity on outbreak preparedness and response. | % of HSAs demonstrating improved knowledge and skills | At least 80% | Activity reports | Every 3 months | M&E Officer |

M&E Plan for Monitoring and Evaluation Program

| Programme Goal: Improve monitoring and evaluation systems within the PHC Department to ensure effective tracking, learning, and Improvement of programs |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective 1: Strengthen the integration and routine use of M&E systems across all PHC programs to support data-driven decision-making and ongoing program improvement by December 2027. |  |  |  |  |  |
| Outputs | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Recruited an M & E Officer | # of M&E Officers recruited | 1 Officer | Department report | Once per year | PHC Director |
| Documented success stories | # of success stories documented | 20 success stories | M&E report | Every 3 months | M&E Officer |
| Conducted review meetings | # of M&E review meetings conducted | 4 meetings | Meeting minutes | Every 3 months | M&E Officer |
| Conducted data quality checks | # of data quality checks | 12 DQCs | Reports | Every month | M&E Officer |
| Conducted baseline surveys | # of Baseline surveys conducted | 2 surveys conducted | Field visits, program reports, photos | Twice per year | M&E Officer |
| Conducted field visits | # of fields visited | 9 field visits conducted | Field visits, program reports, photos | Every 3 months | M&E Officer/Agriculture Team |
| Conducted supervisions | # of supervisions conducted | 12 supervisions | Reports, registers | Every month | M&E Officer |
| Outcomes | Indicator | Target | Data Source (method/tool) | Frequency of data collection | Responsible Person(s) |
| Strengthened M & E systems of the PHC department. | % of PHC programs with functional M & E frameworks implemented and routinely used for decision making | 100% of the PHC Programs | M&E reports, Data review minutes, | Once per year | M&E Officer |